## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Instructions
| Table 1 | Instructions
Instructions
| Table 1 | Instructions
Test Plan
| Table 1 | Test Plan

## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | term-swen-261-sec-letter name
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | JS (3/1)
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | JS (3/1)
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | JS (3/1)
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | JS (3/1)
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | JS (3/1)
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | JS (3/1)
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | JS (3/1)
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | JS (3/1)
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | ACCEPTANCE CRITERION MOVED TO SPRINT 2
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | DM (3/1)
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | DM (3/1)
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | DM (3/1)
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | DM (3/1)
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | DM (3/1)
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | DM (3/1)
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | DM (3/1)
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | DM (3/1)
As a player, I want to move my pieces a single space diagonally so that I can progress the game. | Given I have a piece that can move when I drag the piece to a valid space that is directly adjacent to the piece then the piece is moved to that space. |  |  |  | JS(3/29)
| Given I have a piece that can move when I drag the piece to a valid space that is not directly adjacent to the piece then the piece does not move to that space. |  |  |  | JS(3/29)
| Given I have moved a piece when I want to change my move then I can backtrack the move. |  |  |  | JS(3/29)
| Given I am waiting for my turn when my opponent ends their turn then I can take my turn. |  |  |  | JS(3/29)
As a player, I want to have my piece jump over my opponents piece so that I can capture it, progressing the game. | Given one of my pieces can jump over an enemy piece when I drag my piece over the enemy piece then I capture the enemy's piece. |  |  |  | JS(3/29)
| Given one of my pieces can jump over an enemy piece when I try to make a regular move then the piece will not move. |  |  |  | JS(3/29)
| Given one of my pieces can jump over two different enemy pieces when I make my move then I can pick between jumping over either of the pieces. |  |  |  | JS(3/29)
As a player, I want to have my piece jump over several of my opponents pieces if possible so that I can capture them, progressing the game. | Given I have made a jump move when the piece I moved is able to jump over another piece then I can move my piece to do another jump. |  |  |  | JS(3/29)
| Given I have made a jump move and can make another when I try to submit my turn then the game wont allow the action, forcing me to make the second jump. |  |  |  | JS(3/29)
As a player I want to see the captured piece disappear so that I know that I captured it, removing it from play. | Given I am playing a game of checkers when I jump an opponent's piece then their piece should disappear. and be taken out of play |  |  |  | JS(3/29)
As a player, I want to my piece to become a king piece when it reaches the farthest row so that I can have a king piece. | Given I am in a game when my piece reaches the opposite side of the board then it should transform into a King piece. |  |  |  | JS(3/29)
| Given I am in a game when I get a king piece then it should be able to travel forwards and backwards on the board. |  |  |  | JS(3/29)
| Given I am in a game when my piece becomes a King then I should see a "king" visual on the piece so I know the difference. |  |  |  | JS(3/29)
As a player, I want to take all the enemy pieces so that I can win (or vice versa) and exit the game. | Given there is only one of the opponents pieces left in play when I take said piece then I am given a message indicating I won the game as well as an option to exit the game. | [5 empty] | JS 4/19
| Given there is only one of the my pieces left in play when my opponent takes said piece then I am given a message indicating I lost the game as well as an option to exit the game. | [5 empty] | JS 4/19
| Given the game is over when I press the button to exit the game then I am redirected back to the home screen to begin a new game. | [5 empty] | JS 4/19
As a player, I want to be able to sign out of my current account so that my name can be used by other people. | Given I am signed in on the home page when I press the sign-out button then I should be redirected to the home page as an unsigned in user. | [5 empty] | JS 4/19
| Given I am signed in when I sign out then my name should become available to others looking to play. | [5 empty] | JS 4/19
| Given I am signed in when I sign out then my name should be removed from the 'Online Players' list. | [5 empty] | JS 4/19
| Given I am signed in with an active game when I sign out then I will auto-resign from my current game when I sign out. | [5 empty] | JS 4/19
As a player, I want to be able to resign from a game so that I can end the game early if I want to. | Given I don't want to play a game any more when I resign then I want the game to end. | [5 empty] | JS 4/19
| Given I am playing a game when my opponent resigns then I will get a message saying they resigned. | [5 empty] | JS 4/19
As a Player I want to spectate other people's games so that I can learn from checkers champions. | Given I want to spectate a game when I enter the spectate menu then a list of active games will appear sorted by player win percentage. | [5 empty] | JS 4/19
| Given I want to spectate a game when I click a game in the spectate menu then I see the current state of that game board. | [5 empty] | JS 4/19
| Given I am spectating a game when a player makes a move then my board view will be updated with that move. | [5 empty] | JS 4/19
As a player I want to view my current games so that I can decide which to play. | Given I am in an active game when I go to the home page then I expect to see the games I am currently active in. | [5 empty] | JS 4/19
| Given I am in active games when I click on one game then I get redirected to said game. | [5 empty] | JS 4/19
| Given I am in an active game when I am in one of my games then I expect to see a list of my other active games. | [5 empty] | JS 4/19
| Given I am already in 5 active games when someone attempts to start a game with me (or vice versa) then a game creation error message lets them know that I am already at max active games. | [5 empty] | JS 4/19
| Given I am a signed-in user when I look to the navbar to start a game then I see players sorted by their win rate so I can pick a formidable opponent. | [5 empty] | JS 4/19